## Sheet1
West / East Region
SIEMENS/KUM SHING ENGINEERING CO., LTD. | [7 empty] | Amendment
Daily Work Record of Contractor's Personnel | [11 empty] | DATE : | 2008-11-23
PO NO. | PROJECT | LOCATION | Region | Nature of | Is CP | Name | Safety | Gang | 'H' REW | Commencement | Responsible | Gang Members | Remarks
|  |  |  | Work* | required? | Of | Document |  | Supervisor |  | Engineer
| NO. |  |  | A/B/C/D/J/H | (y/n) | CP In Charge | Holder(LWC/PTW) | Leader | In Charge | Date | (CLPP)
Active Sites
4500471132 ( 3544 New Project ) | TBA | Central Park Dream City S/S - ( 36347-6 ) - L/Tx | ER | J-HV | N | No Needed | No Needed | Ip Ka Chun 98410558 | K W Leung / S H Kwok 63057587 ( J-HW-0540 ) | 23-11-2008 ( 09:00 - 18:00 ) | Robert Tsang | Chung Kwok Wah Yeung Chiu Wing Chum Kok Hang Yan Wai Shing Chan Yeung Lai | 2 x 95 3/C HV Term Panel 4 To L/Tx 1 x 15M x 95 3/C
4500471132 ( 3544 New Project ) | TBA | Central Park Dream City S/S - ( 36347-6 ) - L/Tx | ER | J-LV | N | No Needed | No Needed | Ip Ka Chun 98410558 | K W Leung / S H Kwok 63057587 | 23-11-2008 ( 09:00 - 18:00 ) | Robert Tsang | Chung Kwok Wah Yeung Chiu Wing Chum Kok Hang Yan Wai Shing Chan Yeung Lai | 8 x 960 S/C Term Tx To ACB @ 10M 1 Set x MCT
4500474493 ( 3544 New Project ) | TBA | Wu Kai Sha Station Dev Tower 7 -STTL No 530 - Ma On Shan - ST - ( 36376-2 ) - Tx D1 | ER | J-HV | N | No Needed | No Needed | Ip Ka Chun 98410558 | K W Leung / S H Kwok 63057587 ( J-HW-0528 ) | 18-11-2008 ( 09:00 - 18:00 ) Change The Date From 18-11-2008 To 23-11-2008 | T Y Sin | Chung Kwok Wah Yeung Chiu Wing Chum Kok Hang Yan Wai Shing Chan Yeung Lai | 2 x 95 3/C HV Term Panel 7 To Tx D1 1 x 19M x 95 3/C
4500474488 ( 3544 New Project ) | TBA | Wu Kai Sha Station Dev Tower 1 -STTL No 530 - Ma On Shan - ST - ( 36370-9 ) - Tx D1 | ER | J-HV | N | No Needed | No Needed | Ip Ka Chun 98410558 | K W Leung / S H Kwok 63057587 ( J-HW-0526 ) | 18-11-2008 ( 09:00 - 18:00 ) Change The Date From 15-11-2008 To 23-11-2008 | T Y Sin | Chung Kwok Wah Yeung Chiu Wing Chum Kok Hang Yan Wai Shing Chan Yeung Lai | 2 x 95 3/C HV Term Panel 1 To Tx D1 1 x 20M x 95 3/C
4500474488 ( 3544 New Project ) | TBA | Wu Kai Sha Station Dev Tower 1 -STTL No 530 - Ma On Shan - ST - ( 36370-9 ) - Tx D3 | ER | J-HV | N | No Needed | No Needed | Ip Ka Chun 98410558 | K W Leung / S H Kwok 63057587 ( J-HW-0526 ) | 18-11-2008 ( 09:00 - 18:00 ) Change The Date From 15-11-2008 To 23-11-2008 | T Y Sin | Chung Kwok Wah Yeung Chiu Wing Chum Kok Hang Yan Wai Shing Chan Yeung Lai | 2 x 95 3/C HV Term Panel 3 To Tx D3 1 x 25M x 95 3/C
4500475577 ( 3544 New Project ) | TBA | Wu Kai Sha Station Dev Tower 3A -STTL No 530 - Ma On Shan - ST - ( 36371-6 ) - Tx D1 | ER | J-HV | N | No Needed | No Needed | Ip Ka Chun 98410558 | K W Leung / S H Kwok 63057587 ( J-HW-0527 ) | 18-11-2008 ( 09:00 - 18:00 ) Change The Date From 15-11-2008 To 23-11-2008 | T Y Sin | Chung Kwok Wah Yeung Chiu Wing Chum Kok Hang Yan Wai Shing Chan Yeung Lai | 2 x 95 3/C HV Term Panel 2 To Tx D3 1 x 12M x 95 3/C
DAILY HIRE
A=TRANSPORTATION, B=INSTALLATION, C=TESTING, D= DISMANTLE, J=CABLE JOINTING, H=DAILY HIRE | [11 empty] | Prepared by:
'H' REW = Registed Electrical Worker with work code at H and work code suffix at 0 or 2
(DSP0101008 REV. 0)