## Sheet1
West / East Region
SIEMENS/KUM SHING ENGINEERING CO., LTD.
Daily Work Record of Contractor's Personnel | [11 empty] | DATE : | 2008-11-25
PO NO. | PROJECT | LOCATION | Region | Nature of | Is CP | Name | Safety | Gang | 'H' REW | Commencement | Responsible | Gang Members | Remarks
|  |  |  | Work* | required? | Of | Document |  | Supervisor |  | Engineer
| NO. |  |  | A/B/C/D/J/H | (y/n) | CP In Charge | Holder(LWC/PTW) | Leader | In Charge | Date | (CLPP)
Active Sites
4500495935 ( 3544 New Project ) | TBA | Sai Yeung Choi St 168 S/S - Mong Kok - ( 15290-3 ) - Tx Replacement | WR | J-HV | Y | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | C Y Tse 98197931 ( J-HW-0542 ) | 25-11-2008 ( 23:59 - 05:00 ) | N K Tai | Chung Kwok Wah Yeung Chiu Wing Chum Kok Hang Yan Wai Shing Chan Yeung Lai | Breaking & Remaking 2 x HV Cable Term
4500495935 ( 3544 New Project ) | TBA | Sai Yeung Choi St 168 S/S - Mong Kok - ( 15290-3 ) - Tx Replacement | WR | J-HV | Y | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | C Y Tse 98197931 ( J-HW-0542 ) | 25-11-2008 ( 23:59 - 05:00 ) | N K Tai | Chung Kwok Wah Yeung Chiu Wing Chum Kok Hang Yan Wai Shing Chan Yeung Lai | 2 x 95 3/C HV Term Panel 3 To L/Tx 1 x 9M x 95 3/C
4500495935 ( 3544 New Project ) | TBA | Sai Yeung Choi St 168 S/S - Mong Kok - ( 15290-3 ) - Tx Replacement | WR | J-LV | Y | Kwan Kin Wing 97503319 | Kwan Kin Wing 97503319 | Ng Wing Shuen 91596143 | C K Chu 97536181 | 25-11-2008 ( 23:59 - 05:00 ) | N K Tai | Cheung Fai Kwan Kin Wing Tsang Ku To | Disconnecting & Reconnecting 16 x 960 S/C ( One End )
4500480411 ( 3544-New Project ) | TBA | ICC M3-2 Room N S/S - Jordan - ( 36276-6 ) - Tx D3 | WR | J-LV | N | No Needed | No Needed | Ng Wing Shuen 91596143 | C Y Tse 98197931 ( J-HW-0544 ) | 25-11-2008 ( 09:00 - 18:00 ) | Y K Kwok | Cheung Fai Kwan Kin Wing Tsang Ku To | 12 x 960 S/C Tx D3 To ACB @ 9M 1 Set x MCT
DAILY HIRE
A=TRANSPORTATION, B=INSTALLATION, C=TESTING, D= DISMANTLE, J=CABLE JOINTING, H=DAILY HIRE | [11 empty] | Prepared by:
'H' REW = Registed Electrical Worker with work code at H and work code suffix at 0 or 2
(DSP0101008 REV. 0)