## Sheet1
West / East Region
SIEMENS/KUM SHING ENGINEERING CO., LTD.
Daily Work Record of Contractor's Personnel | [11 empty] | DATE : | 2008-11-26
PO NO. | PROJECT | LOCATION | Region | Nature of | Is CP | Name | Safety | Gang | 'H' REW | Commencement | Responsible | Gang Members | Remarks
|  |  |  | Work* | required? | Of | Document |  | Supervisor |  | Engineer
| NO. |  |  | A/B/C/D/J/H | (y/n) | CP In Charge | Holder(LWC/PTW) | Leader | In Charge | Date | (CLPP)
Active Sites
4500477909 ( 3544-New Project ) | TBA | Kowloon City Rd 199 - To Kwa Wan Hotel S/S - ( 36270-2 ) - Tx D1 | WR | J-LV | Y | Kwan Kin Wing 97503319 | Kwan Kin Wing 97503319 | Ng Wing Shuen 91596143 | C K Chu 97536181 ( J-HW-0536 ) | 26-11-2008 ( 09:00 - 18:00 ) | Y M Wong | Cheung Fai Kwan Kin Wing Tsang Ku To | 16 x 960 S/C Tx D1 To ACB @ 9M 1 Set x MCT
DAILY HIRE
A=TRANSPORTATION, B=INSTALLATION, C=TESTING, D= DISMANTLE, J=CABLE JOINTING, H=DAILY HIRE | [11 empty] | Prepared by:
'H' REW = Registed Electrical Worker with work code at H and work code suffix at 0 or 2
(DSP0101008 REV. 0)