## Sheet1
West / East Region
SIEMENS/KUM SHING ENGINEERING CO., LTD. | [7 empty] | Amendment
Daily Work Record of Contractor's Personnel | [11 empty] | DATE : | 2008-12-12
PO NO. | PROJECT | LOCATION | Region | Nature of | Is CP | Name | Safety | Gang | 'H' REW | Commencement | Responsible | Gang Members | Remarks
|  |  |  | Work* | required? | Of | Document |  | Supervisor |  | Engineer
| NO. |  |  | A/B/C/D/J/H | (y/n) | CP In Charge | Holder(LWC/PTW) | Leader | In Charge | Date | (CLPP)
Active Sites
TBA ( 3544 New Project ) | TBA | Fuk Wah St 188 S/S - SSPo - ( 35932-4 ) - Tx D2 | WR | J-LV | Y | Kwan Kin Wing 97503319 | Kwan Kin Wing 97503319 | Ng Wing Shuen 91596143 | C Y Tse 98197931 ( J-HW-0556 ) | 12-12-2008 ( 09:00 - 19:00 ) | Alex Chow | Cheung Fai Kwan Kin Wing Tsang Ku To | 12 x 960 S/C Tx To ACB @ 13M 1 Set x MCT
TBA ( 3544 New Project ) | TBA | Fuk Wah St 188 S/S - SSPo - ( 35932-4 ) - Tx D2 | WR | J-LV | Y | Kwan Kin Wing 97503319 | Kwan Kin Wing 97503319 | Ng Wing Shuen 91596143 | C Y Tse 98197931 ( J-HW-0556 ) | 12-12-2008 ( 09:00 - 19:00 ) | Alex Chow | Cheung Fai Kwan Kin Wing Tsang Ku To | 4 x 960 S/C Tx To LVB @ 12M
4500486089 ( 3544 New Project ) | TBA | Sau Mau Ping South Est Ph 14 Blk 3 - Sau Sin House - Hui Kwong St - ( 36472-7 ) - Tx D1 | ER | J-HV | N | No Needed | No Needed | Ip Ka Chun 98410558 | K W Leung / S H Kwok 63057587 ( J-HW-0561 ) | 12-12-2008 ( 09:00 - 18:00 ) | Y C Chan | Chung Kwok Wah Yeung Chiu Wing Chum Kok Hang Yan Wai Shing Chan Yeung Lai | 2 x 95 3/C HV Term Panel 2 To Tx D1 1 x 13M x 95 3/C
4500491872 ( 3544 New Project ) | TBA | Sau Mau Ping South Est Ph 13 Blk 5 - Sau Wong House - Hui Kwong St - ( 36454-5 ) - Tx D1 | ER | J-HV | N | No Needed | No Needed | Ip Ka Chun 98410558 | K W Leung / S H Kwok 63057587 ( J-HW-0562 ) | 12-12-2008 ( 09:00 - 18:00 ) | Y C Chan | Chung Kwok Wah Yeung Chiu Wing Chum Kok Hang Yan Wai Shing Chan Yeung Lai | 2 x 95 3/C HV Term Panel 2 To Tx D1 1 x 13M x 95 3/C
4500491872 ( 3544 New Project ) | TBA | Sau Mau Ping South Est Ph 13 Blk 5 - Sau Wong House - Hui Kwong St - ( 36454-5 ) - Tx D2 | ER | J-HV | N | No Needed | No Needed | Ip Ka Chun 98410558 | K W Leung / S H Kwok 63057587 ( J-HW-0562 ) | 12-12-2008 ( 09:00 - 18:00 ) | Y C Chan | Chung Kwok Wah Yeung Chiu Wing Chum Kok Hang Yan Wai Shing Chan Yeung Lai | 2 x 95 3/C HV Term Panel 3 To Tx D2 1 x 15M x 95 3/C
4500491871 ( 3544 New Project ) | TBA | Sau Mau Ping South Est Ph 13 Blk 4 - Sau Ho House - Hui Kwong St - ( 36453-8 ) - Tx D2 | ER | J-HV | N | No Needed | No Needed | Ip Ka Chun 98410558 | K W Leung / S H Kwok 63057587 ( J-HW-0563 ) | 12-12-2008 ( 09:00 - 18:00 ) | Y C Chan | Chung Kwok Wah Yeung Chiu Wing Chum Kok Hang Yan Wai Shing Chan Yeung Lai | 2 x 95 3/C HV Term Panel 1 To Tx D2 1 x 12M x 95 3/C
4500491871 ( 3544 New Project ) | TBA | Sau Mau Ping South Est Ph 13 Blk 4 - Sau Ho House - Hui Kwong St - ( 36453-8 ) - Tx D1 | ER | J-HV | N | No Needed | No Needed | Ip Ka Chun 98410558 | K W Leung / S H Kwok 63057587 ( J-HW-0563 ) | 12-12-2008 ( 09:00 - 18:00 ) | Y C Chan | Chung Kwok Wah Yeung Chiu Wing Chum Kok Hang Yan Wai Shing Chan Yeung Lai | 2 x 95 3/C HV Term Panel 2 To Tx D1 1 x 15M x 95 3/C
DAILY HIRE
A=TRANSPORTATION, B=INSTALLATION, C=TESTING, D= DISMANTLE, J=CABLE JOINTING, H=DAILY HIRE | [11 empty] | Prepared by:
'H' REW = Registed Electrical Worker with work code at H and work code suffix at 0 or 2
(DSP0101008 REV. 0)