## Sheet1
West / East Region
SIEMENS/KUM SHING ENGINEERING CO., LTD.
Daily Work Record of Contractor's Personnel | [11 empty] | DATE : | 2008-12-13
PO NO. | PROJECT | LOCATION | Region | Nature of | Is CP | Name | Safety | Gang | 'H' REW | Commencement | Responsible | Gang Members | Remarks
|  |  |  | Work* | required? | Of | Document |  | Supervisor |  | Engineer
| NO. |  |  | A/B/C/D/J/H | (y/n) | CP In Charge | Holder(LWC/PTW) | Leader | In Charge | Date | (CLPP)
Active Sites
TBA ( 3544 New Project ) | TBA | HK Obsepvatory B S/S - TST - ( 02098-2 ) - | WR | J-LV | Y | Kwan Kin Wing 97503319 | Kwan Kin Wing 97503319 | Ng Wing Shuen 91596143 | Michael Tang 94228077 ( J-HW-0555 ) | 13-12-2008 ( 09:00 - 19:00 ) | F K Yip | Cheung Fai Kwan Kin Wing Tsang Ku To | Disconnecting & Removing 7 x 960 S/C Tx To ACB
TBA ( 3544 New Project ) | TBA | HK Obsepvatory B S/S - TST - ( 02098-2 ) - | WR | J-LV | Y | Kwan Kin Wing 97503319 | Kwan Kin Wing 97503319 | Ng Wing Shuen 91596143 | Michael Tang 94228077 ( J-HW-0555 ) | 13-12-2008 ( 09:00 - 19:00 ) | F K Yip | Cheung Fai Kwan Kin Wing Tsang Ku To | 12 x 960 S/C Tx To ACB @ 10M 1 Set x MCT
TBA ( 3544 New Project ) | TBA | Chun Seen Mei Chuen A S/S - ( 02216-2 ) - L/Tx | WR | J-LV | Y | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Michael Tang 94228077 | 13-12-2008 ( 11:00 - 15:00 ) | C L Wong | Chung Kwok Wah Yeung Chiu Wing Chum Kok Hang Yan Wai Shing Chan Yeung Lai | Disconnecting 8 x 960 S/C ( One End )
DAILY HIRE
A=TRANSPORTATION, B=INSTALLATION, C=TESTING, D= DISMANTLE, J=CABLE JOINTING, H=DAILY HIRE | [11 empty] | Prepared by:
'H' REW = Registed Electrical Worker with work code at H and work code suffix at 0 or 2
(DSP0101008 REV. 0)