## Sheet1
West / East Region
SIEMENS/KUM SHING ENGINEERING CO., LTD. | [7 empty] | Amendment
Daily Work Record of Contractor's Personnel | [11 empty] | DATE : | 2008-12-20
PO NO. | PROJECT | LOCATION | Region | Nature of | Is CP | Name | Safety | Gang | 'H' REW | Commencement | Responsible | Gang Members | Remarks
|  |  |  | Work* | required? | Of | Document |  | Supervisor |  | Engineer
| NO. |  |  | A/B/C/D/J/H | (y/n) | CP In Charge | Holder(LWC/PTW) | Leader | In Charge | Date | (CLPP)
Active Sites
TBA ( 3544 New Project ) ( Cancelled ) | TBA | Chun Seen Mei Chuen A S/S - ( 02216-2 ) - L/Tx | WR | J-LV | Y | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Michael Tang 94228077 | 20-12-2008 ( 14:00 - 15:00 ) | C L Wong | Chung Kwok Wah Yeung Chiu Wing Chum Kok Hang Yan Wai Shing Chan Yeung Lai | Reconnecting 8 x 960 S/C ( One End )
4500491871 ( 3544 New Project ) | TBA | Sau Mau Ping South Eat Ph 13 Blk 4 - San Ho House S/S - ( 36453-8 ) - Tx D1 | ER | J-LV | N | No Needed | No Needed | Ng Wing Shuen 91596143 | K W Leung / S H Kwok 63057587 ( J-HW-0566 ) | 20-12-2008 ( 09:00 - 19:00 ) | Robert Tsang | Cheung Fai Kwan Kin Wing Tsang Ku To | 12 x 960 S/C Tx To ACB @ 10M ( 1 Set x MCT )
4500492168 ( 3544 New Project ) | TBA | New Trend Centre S/S - San Po Kong - ( 15822-7 ) - Panel 02 & Panel 03 | ER | J-HV | Y | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | K W Leung / S H Kwok 63057587 | 20-12-2008 ( 23:59 - 06:00 ) | W K Kowk | Chung Kwok Wah Yeung Chiu Wing Chum Kok Hang Yan Wai Shing Chan Yeung Lai | Breaking & Remaking 2 x HV Term Panel 02 & Panel 03 For Busbar Extension
DAILY HIRE
A=TRANSPORTATION, B=INSTALLATION, C=TESTING, D= DISMANTLE, J=CABLE JOINTING, H=DAILY HIRE | [11 empty] | Prepared by:
'H' REW = Registed Electrical Worker with work code at H and work code suffix at 0 or 2
(DSP0101008 REV. 0)