## Sheet1
West / East Region
SIEMENS/KUM SHING ENGINEERING CO., LTD.
Daily Work Record of Contractor's Personnel | [11 empty] | DATE : | 2009-03-05
PO NO. | PROJECT | LOCATION | Region | Nature of | Is CP | Name | Safety | Gang | 'H' REW | Commencement | Responsible | Gang Members | Remarks
|  |  |  | Work* | required? | Of | Document |  | Supervisor |  | Engineer
| NO. |  |  | A/B/C/D/J/H | (y/n) | CP In Charge | Holder(LWC/PTW) | Leader | In Charge | Date | (CLPP)
Active Sites
4500458958 ( 3544 New Project ) | TBA | Upper Ngau Tau Kok Blk 1 - Sheung Hing House S/S - ( 36287-8 ) - Tx D2 | ER | J-HV | Y | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | K W Leung / S H Kwok 63057587 ( J-HW-0682 ) | 05-03-2009 ( 09:00 - 14:00 ) | Y C Chan | Chung Kwok Wah Yeung Chiu Wing Chum Kok Hang Yan Wai Shing Chan Yeung Lai | 2 x 95 3/C HV Term P2 To Tx D2 1 x 16M x 95 3/C
4500458451 ( 3544 New Project ) | TBA | Upper Ngau Tau Kok Blk 2 - Sheung Shing House S/S - ( 36288-5 ) - Tx D5 | ER | J-HV | Y | K W Chung 90936833 | K W Chung 90936833 | Ip Ka Chun 98410558 | K W Leung / S H Kwok 63057587 ( J-HW-0683 ) | 05-03-2009 ( 09:00 - 14:00 ) | Y C Chan | Chung Kwok Wah Yeung Chiu Wing Chum Kok Hang Yan Wai Shing Chan Yeung Lai | 2 x 95 3/C HV Term P1 To Tx D5 1 x 23M x 95 3/C
4500464730 ( 3544 New Project ) | TBA | Upper Ngau Tau Kok Blk 3 - Sheung Fu House S/S - ( 36289-2 ) - Tx D8 | ER | J-HV | Y | Y L Chan 69705055 | Y L Chan 69705055 | Ip Ka Chun 98410558 | K W Leung / S H Kwok 63057587 ( J-HW-0684 ) | 05-03-2009 ( 09:00 - 14:00 ) | Y C Chan | Chung Kwok Wah Yeung Chiu Wing Chum Kok Hang Yan Wai Shing Chan Yeung Lai | 2 x 95 3/C HV Term P1 To Tx D8 1 x 18M x 95 3/C
DAILY HIRE
A=TRANSPORTATION, B=INSTALLATION, C=TESTING, D= DISMANTLE, J=CABLE JOINTING, H=DAILY HIRE | [11 empty] | Prepared by:
'H' REW = Registed Electrical Worker with work code at H and work code suffix at 0 or 2
(DSP0101008 REV. 0)