## Sheet1
West / East Region
SIEMENS/KUM SHING ENGINEERING CO., LTD.
Daily Work Record of Contractor's Personnel | [11 empty] | DATE : | 2009-03-07
PO NO. | PROJECT | LOCATION | Region | Nature of | Is CP | Name | Safety | Gang | 'H' REW | Commencement | Responsible | Gang Members | Remarks
|  |  |  | Work* | required? | Of | Document |  | Supervisor |  | Engineer
| NO. |  |  | A/B/C/D/J/H | (y/n) | CP In Charge | Holder(LWC/PTW) | Leader | In Charge | Date | (CLPP)
Active Sites
4500511414 ( 3544 New Project ) | TBA | Cathay Pacific Staff Hotel S/S - ( 18025-6 ) - Tx D3 | WR | J-LV | Y | K W Kwan 97503319 | K W Kwan 97503319 | Ng Wing Shuen 91596143 | C Y Tse 98197931 C K Chu 97536168 ( J-HW-0689 ) | 07-03-2009 ( 13:00 - 01:00 ) | S M Kwong | Cheung Fai Kwan Kin Wing Tsang Ku To | 12 x 960 S/C LVB To ACB @ 12M ( 1 Set x MCT )
4500511414 ( 3544 New Project ) | TBA | Cathay Pacific Staff Hotel S/S - ( 18025-6 ) - Tx D3 | WR | J-LV | Y | K W Kwan 97503319 | K W Kwan 97503319 | Ng Wing Shuen 91596143 | C Y Tse 98197931 C K Chu 97536168 ( J-HW-0689 ) | 07-03-2009 ( 13:00 - 01:00 ) | S M Kwong | Cheung Fai Kwan Kin Wing Tsang Ku To | 12 x 960 S/C Tx D1 To LVB @ 14M
DAILY HIRE
A=TRANSPORTATION, B=INSTALLATION, C=TESTING, D= DISMANTLE, J=CABLE JOINTING, H=DAILY HIRE | [11 empty] | Prepared by:
'H' REW = Registed Electrical Worker with work code at H and work code suffix at 0 or 2
(DSP0101008 REV. 0)