## Sheet1
West / East Region
SIEMENS/KUM SHING ENGINEERING CO., LTD. | [7 empty] | Amendment
Daily Work Record of Contractor's Personnel | [11 empty] | DATE : | 2009-03-21
PO NO. | PROJECT | LOCATION | Region | Nature of | Is CP | Name | Safety | Gang | 'H' REW | Commencement | Responsible | Gang Members | Remarks
|  |  |  | Work* | required? | Of | Document |  | Supervisor |  | Engineer
| NO. |  |  | A/B/C/D/J/H | (y/n) | CP In Charge | Holder(LWC/PTW) | Leader | In Charge | Date | (CLPP)
Active Sites
TBA ( 3544 New Project ) | TBA | Nathan Rd 63 E S/S - Lock Rd ( 36499-8 ) - Tx D12 | WR | J-LV | N | No Needed | No Needed | Ng Wing Shuen 91596143 | C Y Tse 98197931 C K Chu 97536168 | 20-03-2009 ( 09:00 - 19:00 ) Change The Date From 21-03-2009 To 20-03-2009 | Alex Chow | Cheung Fai Kwan Kin Wing Tsang Ku To | 12 x 960 S/C Tx D12 To ACB @ M ( 1 Set x MCT )
4500512565 ( 3544 New Project ) | TBA | Nathan Rd 63 F S/S - Lock Rd ( 36497-5 ) - Tx D16 | WR | J-LV | N | No Needed | No Needed | Ng Wing Shuen 91596143 | C Y Tse 98197931 C K Chu 97536168 | 20-03-2009 ( 09:00 - 19:00 ) Change The Date From 21-03-2009 To 20-03-2009 | Alex Chow | Cheung Fai Kwan Kin Wing Tsang Ku To | 12 x 960 S/C Tx D16 To ACB @ M ( 1 Set x MCT )
4500502934 ( 3544 New Project ) | TBA | KCRC Beacon Hill Bldg B S/S - ( 35778-7 ) - Panel 3 | NR | J-HV | Y | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | H P Chan 94923621 | 21-03-2009 ( 01:00 - 04:00 ) | W L Chan | Chung Kwok Wah Yeung Chiu Wing Chum Kok Hang Yan Wai Shing Chan Yeung Lai | Breaking & Remarking 2 x HV Term P3 For Busbus Extension
4500512561 ( 3544 New Project ) | TBA | Nathan Rd 63 C S/S - Lock Rd ( 36495-8 ) - Tx D8 | WR | J-HV | N | No Needed | No Needed | Ip Ka Chun 98410558 | C Y Tse 98197931 C K Chu 97536168 ( J-HW-0699 ) | 21-03-2009 ( 09:00 - 19:00 ) | Alex Chow | Chung Kwok Wah Yeung Chiu Wing Chum Kok Hang Yan Wai Shing Chan Yeung Lai | 2 x 95 3/C HV Term Bd B - P2 To Tx D8 1 x ?M x 95 3/C
4500512562 ( 3544 New Project ) | TBA | Nathan Rd 63 D S/S - Lock Rd ( 36496-8 ) - Tx D9 | WR | J-HV | N | No Needed | No Needed | W S Lau 92815715 | C Y Tse 98197931 C K Chu 97536168 ( J-HW-0700 ) | 21-03-2009 ( 09:00 - 19:00 ) | Alex Chow | Chan Hei Long Tsang Man Kit Cheng Kin On Ip Wai Kit Li Kai Chung | 2 x 95 3/C HV Term Bd A - P3 To Tx D9 1 x ?M x 95 3/C
4500512562 ( 3544 New Project ) | TBA | Nathan Rd 63 D S/S - Lock Rd ( 36496-8 ) - Tx D10 | WR | J-HV | N | No Needed | No Needed | W S Lau 92815715 | C Y Tse 98197931 C K Chu 97536168 ( J-HW-0700 ) | 21-03-2009 ( 09:00 - 19:00 ) | Alex Chow | Chan Hei Long Tsang Man Kit Cheng Kin On Ip Wai Kit Li Kai Chung | 2 x 95 3/C HV Term Bd B - P5 To Tx D10 1 x ?M x 95 3/C
4500502934 ( 3544 New Project ) | TBA | KCRC Beacon Hill Bldg B S/S - ( 35778-7 ) - Panel 3 | NR | J-HV | Y | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | H P Chan 94923621 | 21-03-2009 ( 01:00 - 04:00 ) | W L Chan | Chung Kwok Wah Yeung Chiu Wing Chum Kok Hang Yan Wai Shing Chan Yeung Lai | Breaking & Remarking 1 x HV Term P3 For Busbus Extension
4500373349 ( 1207 Old Project ) | TBA | Skypier B S/S - CLK ( 35671-2 ) - Tx D3 | WR | J-LV | N | No Needed | No Needed | Ip Ka Chun 98410558 | C Y Tse 98197931 C K Chu 97536168 | 21-03-2009 ( 09:00 - 19:00 ) | C W Lee | Chung Kwok Wah Yeung Chiu Wing Chum Kok Hang Yan Wai Shing Chan Yeung Lai | 12 x 960 S/C Tx D3 To ACB @ 8M ( 1 Set x MCT )
4500373349 ( 1207 Old Project ) | TBA | Skypier B S/S - CLK ( 35671-2 ) - Tx D4 | WR | J-LV | N | No Needed | No Needed | Ng Wing Shuen 91596143 | C Y Tse 98197931 C K Chu 97536168 | 21-03-2009 ( 09:00 - 19:00 ) | C W Lee | Cheung Fai Kwan Kin Wing Tsang Ku To | 12 x 960 S/C Tx D4 To LVB @ 15M ( 1 Set x MCT )
TBA ( 3544 New Project ) | TBA | Honour Bldg S/S - Sheung Heung Rd 64 - 78 ( 02309-6 ) - Tx Replacement | WR | J-LV | Y | K W Kwan 97503319 | K W Kwan 97503319 | Ng Wing Shuen 91596143 | C Y Tse 98197931 C K Chu 97536168 | 21-02-2009 ( 23:30 - 08:00 ) | Alex Sien | Cheung Fai Kwan Kin Wing Tsang Ku To | Disconnecting & Removing 14 x 960 S/C Tx To ACB & To LVB
TBA ( 3544 New Project ) | TBA | Honour Bldg S/S - Sheung Heung Rd 64 - 78 ( 02309-6 ) - Tx Replacement | WR | J-LV | Y | K W Kwan 97503319 | K W Kwan 97503319 | Ng Wing Shuen 91596143 | C Y Tse 98197931 C K Chu 97536168 | 21-02-2009 ( 23:30 - 08:00 ) | Alex Sien | Cheung Fai Kwan Kin Wing Tsang Ku To | 10 x 960 S/C Tx To ACB @ 12M 1 Set x MCT
TBA ( 3544 New Project ) | TBA | Honour Bldg S/S - Sheung Heung Rd 64 - 78 ( 02309-6 ) - Tx Replacement | WR | J-LV | Y | K W Kwan 97503319 | K W Kwan 97503319 | Ng Wing Shuen 91596143 | C Y Tse 98197931 C K Chu 97536168 | 21-02-2009 ( 23:30 - 08:00 ) | Alex Sien | Cheung Fai Kwan Kin Wing Tsang Ku To | 4 x 960 S/C Tx To LVB @ 10M
DAILY HIRE
A=TRANSPORTATION, B=INSTALLATION, C=TESTING, D= DISMANTLE, J=CABLE JOINTING, H=DAILY HIRE | [11 empty] | Prepared by:
'H' REW = Registed Electrical Worker with work code at H and work code suffix at 0 or 2
(DSP0101008 REV. 0)