## Sheet1
West / East Region
SIEMENS/KUM SHING ENGINEERING CO., LTD. | [7 empty] | Amendment
Daily Work Record of Contractor's Personnel | [11 empty] | DATE : | 2009-03-25
PO NO. | PROJECT | LOCATION | Region | Nature of | Is CP | Name | Safety | Gang | 'H' REW | Commencement | Responsible | Gang Members | Remarks
|  |  |  | Work* | required? | Of | Document |  | Supervisor |  | Engineer
| NO. |  |  | A/B/C/D/J/H | (y/n) | CP In Charge | Holder(LWC/PTW) | Leader | In Charge | Date | (CLPP)
Active Sites
4500493452 ( 3544 New Project ) | TBA | Pak Tin Children Centre S/S - Cornwall St - ( 36258-1 ) | EWR | J-LV | N | No Needed | No Needed | Ng Wing Shuen 91596143 | C Y Tse 98197931 C K Chu 97536168 | 25-03-2009 ( 09:00 - 18:00 ) | C Y Chan | Cheung Fai Kwan Kin Wing Tsang Ku To | 12 x 960 S/C LVB To ACB @ 14M ( 1 Set x MCT )
4500493452 ( 3544 New Project ) | TBA | Pak Tin Children Centre S/S - Cornwall St - ( 36258-1 ) | EWR | J-HV | N | No Needed | No Needed | Ip Ka Chun 98410558 | C Y Tse 98197931 C K Chu 97536168 ( J-HW-0701 ) | 25-03-2009 ( 14:00 - 18:00 ) Change The Date From 26-03-2009 To 25-03-2009 | C Y Chan | Chung Kwok Wah Yeung Chiu Wing Chum Kok Hang Yan Wai Shing Chan Yeung Lai | 2 x 95 3/C HV Term P1 To L/Tx 1 x 12M x 95 3/C
DAILY HIRE
A=TRANSPORTATION, B=INSTALLATION, C=TESTING, D= DISMANTLE, J=CABLE JOINTING, H=DAILY HIRE | [11 empty] | Prepared by:
'H' REW = Registed Electrical Worker with work code at H and work code suffix at 0 or 2
(DSP0101008 REV. 0)