## Sheet1
West / East Region
SIEMENS/KUM SHING ENGINEERING CO., LTD. | [7 empty] | Amendment
Daily Work Record of Contractor's Personnel | [11 empty] | DATE : | 2009-08-06
PO NO. | PROJECT | LOCATION | Region | Nature of | Is CP | Name | Safety | Gang | 'H' REW | Commencement | Responsible | Gang Members | Remarks
|  |  |  | Work* | required? | Of | Document |  | Supervisor |  | Engineer
| NO. |  |  | A/B/C/D/J/H | (y/n) | CP In Charge | Holder(LWC/PTW) | Leader | In Charge | Date | (CLPP)
Active Sites
4500522637 ( 3544 New Project ) | TBA | ICC Room Z ( 50/F ) S/S - Jordan - ( 36266-1 ) - Tx D1 ( Tx D58 ) | EWR | J-LV | Y | K W Kwan 97503319 | K W Kwan 97503319 | Ng Wing Shuen 91596143 | C Y Tse 98197931 C K Chu 97536168 | 06/08/2009 ( 09:00 - 19:00 ) | Y K Kwok | Cheung Fai Kwan Kin Wing Tsang Ku To | 12 x 960 S/C Tx D1 To ACB @ ?M 1 Set x MCT
TBA ( Siemens Project ) | TBA | Tai Yip St 27 S/S - Wing Ying I/B S/S - | EWR | J - HV | Y | K W Chung 90306833 | K W Chung 90306833 | K W Chung 90306833 | Donny Wong 92831602 ( J-HW-0785 ) | 06/08/2009 ( 09:00 - 14:00 ) | K L Leung | Yan Wai Shing | B/R 1 x HV Term For CVT Replacement
4500533106 ( 3544 New Project ) | TBA | J/O Hoi Kok St / Hoi Ming St S/S - TW - ( 36628-3 ) - L/Tx | EWR | J-LV | N | No Needed | No Needed | Ip Ka Chun 98410558 | C Y Tse 98197931 C K Chu 97536168 | 06/08/2009 ( 09:00 - 17:00 ) Change The Date From 08-08-2009 To 06-08-2009 | Raymond Sze | Chum Kok Hang Yan Wai Shing Chan Yeung Lai Yeung Chiu Wing Ip Ka Chun | 4 x 960 S/C L/Tx To ACB @ 8M 1 Set x MCT
DAILY HIRE
A=TRANSPORTATION, B=INSTALLATION, C=TESTING, D= DISMANTLE, J=CABLE JOINTING, H=DAILY HIRE | [11 empty] | Prepared by:
'H' REW = Registed Electrical Worker with work code at H and work code suffix at 0 or 2
(DSP0101008 REV. 0)