## Sheet1
West / East Region
SIEMENS/KUM SHING ENGINEERING CO., LTD. | [7 empty] | Amentmend
Daily Work Record of Contractor's Personnel | [11 empty] | DATE : | 2009-08-08
PO NO. | PROJECT | LOCATION | Region | Nature of | Is CP | Name | Safety | Gang | 'H' REW | Commencement | Responsible | Gang Members | Remarks
|  |  |  | Work* | required? | Of | Document |  | Supervisor |  | Engineer
| NO. |  |  | A/B/C/D/J/H | (y/n) | CP In Charge | Holder(LWC/PTW) | Leader | In Charge | Date | (CLPP)
Active Sites
4500522637 ( 3544 New Project ) | TBA | ICC Room Z ( 50/F ) S/S - Jordan - ( 36266-1 ) - Tx D3 ( Tx D60 ) | EWR | J-LV | Y | K W Kwan 97503319 | K W Kwan 97503319 | Ng Wing Shuen 91596143 | C Y Tse 98197931 C K Chu 97536168 | 08/08/2009 ( 09:00 - 17:00 ) Change The Date From 08-08-2009 To 12-08-2009 | Y K Kwok | Cheung Fai Kwan Kin Wing Tsang Ku To | 12 x 960 S/C Tx D3 To ACB @ ?M 1 Set x MCT
4500533106 ( 3544 New Project ) | TBA | J/O Hoi Kok St / Hoi Ming St S/S - TW - ( 36628-3 ) - L/Tx | EWR | J-LV | N | No Needed | No Needed | K W Chung 90306833 | C Y Tse 98197931 C K Chu 97536168 | 08/08/2009 ( 09:00 - 17:00 ) Change The Date From 08-08-2009 To 06-08-2009 | Raymond Sze | Chum Kok Hang Yan Wai Shing Chan Yeung Lai Yeung Chiu Wing Ip Ka Chun | 4 x 960 S/C L/Tx To ACB @ 8M 1 Set x MCT
4500502712 ( 3544 New Project ) | TBA | Regent Centre C S/S - Ta Chuen Ping St - TW - ( 16276-4 ) - Tx D7 | EWR | J-LV | Y | K W Kwan 97503319 | K W Kwan 97503319 | Ng Wing Shuen 91596143 | C Y Tse 98197931 C K Chu 97536168 | 08/08/2009 ( 09:00 - 18:00 ) | C F Tam | Cheung Fai Kwan Kin Wing Tsang Ku To | 12 x 960 S/C Tx D7 To ACB @ 9M 1 Set x MCT
TBA ( 3544 New Project ) | TBA | CU Hotel And Tourism School S/S - ( 36603-8 ) - Tx D1 | EWR | J-HV | N | No Needed | No Needed | K W Chung 90306833 | K W Leung / S H Kwok 63057587 ( J-HW-0811 ) | 08/08/2009 ( 10:00 - 18:00 ) |  | Chum Kok Hang Yan Wai Shing Chan Yeung Lai Yeung Chiu Wing Ip Ka Chun | 2 x 95 3/C HV Term P1 To Tx D1 1 x 19M x 95 3/C
TBA ( 3544 New Project ) | TBA | CU Hotel And Tourism School S/S - ( 36603-8 ) - Tx D2 | EWR | J-HV | N | No Needed | No Needed | K W Chung 90306833 | K W Leung / S H Kwok 63057587 ( J-HW-0811 ) | 08/08/2009 ( 10:00 - 18:00 ) |  | Chum Kok Hang Yan Wai Shing Chan Yeung Lai Yeung Chiu Wing Ip Ka Chun | 2 x 95 3/C HV Term P2 To Tx D2 1 x 16M x 95 3/C
DAILY HIRE
A=TRANSPORTATION, B=INSTALLATION, C=TESTING, D= DISMANTLE, J=CABLE JOINTING, H=DAILY HIRE | [11 empty] | Prepared by:
'H' REW = Registed Electrical Worker with work code at H and work code suffix at 0 or 2
(DSP0101008 REV. 0)