## Sheet1
West / East Region
SIEMENS/KUM SHING ENGINEERING CO., LTD. | [7 empty] | Amendment
Daily Work Record of Contractor's Personnel | [11 empty] | DATE : | 2009-08-12
PO NO. | PROJECT | LOCATION | Region | Nature of | Is CP | Name | Safety | Gang | 'H' REW | Commencement | Responsible | Gang Members | Remarks
|  |  |  | Work* | required? | Of | Document |  | Supervisor |  | Engineer
| NO. |  |  | A/B/C/D/J/H | (y/n) | CP In Charge | Holder(LWC/PTW) | Leader | In Charge | Date | (CLPP)
Active Sites
4500522638 ( 3544 New Project ) | TBA | ICC Room A-A ( 50/F ) S/S - Jordan - ( 36267-9 ) - Tx D3 ( Tx D63 ) | EWR | J-LV | Y | K W Kwan 97503319 | K W Kwan 97503319 | Ng Wing Shuen 91596143 | C Y Tse 98197931 C K Chu 97536168 | 12/08/2009 ( 09:00 - 19:00 ) | Y K Kwok | Cheung Fai Kwan Kin Wing Tsang Ku To | 12 x 960 S/C Tx D3 To ACB @ ?M 1 Set x MCT
TBA ( Siemens Project ) | TBA | Lei Muk Shue Ph3 Comm S/S - ( 33147-8 ) | EWR | J - HV | Y | K W Chung 90306833 | K W Chung 90306833 | K W Chung 90306833 | Donny Wong 92831602 ( J-HW-0795 ) | 12/08/2009 ( 09:00 - 14:00 ) | S K Chow | Yan Wai Shing | B/R 1 x HV Term For CVT Replacement
TBA ( Siemens Project ) | TBA | Lai Chi Kok Ph4 Primary School S/S - ( 30847-2 ) - ( Circuit On Lai Ying House A ) | EWR | J - HV | Y | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Donny Wong 92831602 ( J-HW-0796 ) | 12/08/2009 ( 09:00 - 14:00 ) |  | Chum Kwok Hang | B/R 1 x HV Term For CVT Replacement
4500522637 ( 3544 New Project ) | TBA | ICC Room Z ( 50/F ) S/S - Jordan - ( 36266-1 ) - Tx D3 ( Tx D60 ) | EWR | J-LV | Y | K W Kwan 97503319 | K W Kwan 97503319 | Ng Wing Shuen 91596143 | C Y Tse 98197931 C K Chu 97536168 | 12/08/2009 ( 09:00 - 17:00 ) Change The Date From 08-08-2009 To 12-08-2009 | Y K Kwok | Cheung Fai Kwan Kin Wing Tsang Ku To | 12 x 960 S/C Tx D3 To ACB @ ?M 1 Set x MCT
DAILY HIRE
A=TRANSPORTATION, B=INSTALLATION, C=TESTING, D= DISMANTLE, J=CABLE JOINTING, H=DAILY HIRE | [11 empty] | Prepared by:
'H' REW = Registed Electrical Worker with work code at H and work code suffix at 0 or 2
(DSP0101008 REV. 0)