## Sheet1
West / East Region
SIEMENS/KUM SHING ENGINEERING CO., LTD. | [7 empty] | Amendment
Daily Work Record of Contractor's Personnel | [11 empty] | DATE : | 2009-08-17
PO NO. | PROJECT | LOCATION | Region | Nature of | Is CP | Name | Safety | Gang | 'H' REW | Commencement | Responsible | Gang Members | Remarks
|  |  |  | Work* | required? | Of | Document |  | Supervisor |  | Engineer
| NO. |  |  | A/B/C/D/J/H | (y/n) | CP In Charge | Holder(LWC/PTW) | Leader | In Charge | Date | (CLPP)
Active Sites
TBA ( Siemens Project ) | TBA | Mei Tak Fty Bldg A S/S - Wong"s I/C C S/S | EWR | J - HV | Y | K W Chung 90306833 | K W Chung 90306833 | K W Chung 90306833 | Donny Wong 92831602 ( J-HW-0788 ) | 17/08/2009 ( 09:00 - 14:00 ) | K L Leung | Yan Wai Shing | B/R 1 x HV Term For CVT Replacement
TBA ( Siemens Project ) | TBA | VTC Yeo Chi Man Secondary School S/S - ( 34482-9 ) - | EWR | J - HV | Y | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Donny Wong 92831602 ( J-HW-0811 ) | 17/08/2009 ( 09:00 - 14:00 ) | Jammy Ng | Chum Kwok Hang | B/R 1 x HV Term For CVT Replacement
TBA ( Siemens Project ) | TBA | SKH - TKO - Kei Tak Primary School S/S - ( 34484-3 ) - | EWR | J - HV | Y | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Donny Wong 92831602 ( J-HW-0811 ) | 17/08/2009 ( 14:00 - 17:00 ) | Jammy Ng | Chum Kwok Hang | B/R 1 x HV Term For CVT Replacement
4500522869 ( 3544 New Project ) | TBA | ICC M4-2 Room T S/S - Jordan - ( 36589-1 ) - Tx D1 | EWR | J-LV | N | No Needed | No Needed | Ng Wing Shuen 91596143 | C Y Tse 98197931 C K Chu 97536168 | 17/08/2009 ( 09:00 - 19:00 ) | Y K Kwok | Cheung Fai Kwan Kin Wing Tsang Ku To | 16 x 960 S/C ACB Side Only @ ?M 1 Set x MCT
DAILY HIRE
A=TRANSPORTATION, B=INSTALLATION, C=TESTING, D= DISMANTLE, J=CABLE JOINTING, H=DAILY HIRE | [11 empty] | Prepared by:
'H' REW = Registed Electrical Worker with work code at H and work code suffix at 0 or 2
(DSP0101008 REV. 0)