## Sheet1
West / East Region
SIEMENS/KUM SHING ENGINEERING CO., LTD. | [7 empty] | Amendment
Daily Work Record of Contractor's Personnel | [11 empty] | DATE : | 2009-08-25
PO NO. | PROJECT | LOCATION | Region | Nature of | Is CP | Name | Safety | Gang | 'H' REW | Commencement | Responsible | Gang Members | Remarks
|  |  |  | Work* | required? | Of | Document |  | Supervisor |  | Engineer
| NO. |  |  | A/B/C/D/J/H | (y/n) | CP In Charge | Holder(LWC/PTW) | Leader | In Charge | Date | (CLPP)
Active Sites
TBA ( Siemens Project ) Cancelled | TBA | Lai Yip St 50 - S/S - NTK-011 - S/S | EWR | J - HV | Y | K W Chung 90306833 | K W Chung 90306833 | K W Chung 90306833 | Donny Wong 92831602 ( J-HW-0790 ) | 25/08/2009 ( 09:00 - 14:00 ) |  | Chum Kwok Hang | B/R 1 x HV Term For CVT Replacement
TBA Siemens Project | TBA | Ngau Tau Kok Comm Centre - S/S ( 01623-5 ) Circuit On : Kay Yan House | EWR | J - HV | Y | K W Chung 90306833 | K W Chung 90306833 | K W Chung 90306833 | Donny Wong 92831602 ( J-HW-0790 ) | 25/08/2009 ( 09:00 - 14:00 ) |  | Yan Wai Shing | B/R 1 x HV Term For CVT Replacement
TBA Siemens Project | TBA | HK Standard Test S/S-( 08802-9 ) Circuit On : Chen Hosong | NR | J - HV | Y | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Donny Wong 92831602 ( J-HW-0821 ) | 25/08/2009 ( 09:00 - 14:00 ) |  | Chum Kwok Hang | B/R 1 x HV Term For CVT Replacement
4500516559 ( 3544 New Project ) | TBA | Nathan Rd 63 A S/S - TST - ( 36593-2 ) - Tx D1 | EWR | J-LV | N | No Needed | No Needed | Ng Wing Shuen 91596143 | C Y Tse 98197931 C K Chu 97536168 | 25/08/2009 ( 09:00 - 19:00 ) | Alex Chow | Cheung Fai Kwan Kin Wing Tsang Ku To | 12 x 960 S/C Tx D1 To ACB @ ?M 1 Set x MCT ( ACB Only )
4500516559 ( 3544 New Project ) | TBA | Nathan Rd 63 A S/S - TST - ( 36593-2 ) - Tx D2 | EWR | J-LV | N | No Needed | No Needed | Ng Wing Shuen 91596143 | C Y Tse 98197931 C K Chu 97536168 | 25/08/2009 ( 09:00 - 19:00 ) | Alex Chow | Cheung Fai Kwan Kin Wing Tsang Ku To | 12 x 960 S/C Tx D1 To ACB @ ?M 1 Set x MCT ( ACB Only )
TBA ( 3544 New Project ) | TBA | Tsang Tai Uk PKG A S/S - Shatin - ( 36704-1 ) - L/Tx | NR | J-HV | N | C W Yeung 61732638 | C W Yeung 61732638 | W S Yan Chung 94606064 | C Y Tse 98197931 C K Chu 97536168 ( J-HW-0825 ) | 25/08/2009 ( 15:00 - 19:00 ) | T Y Sin | Chum Kok Hang Yan Wai Shing Chan Yeung Lai | 2 x 95 S/C HV Term P3 To L/Tx 3 x 7M x 95 S/C
DAILY HIRE
A=TRANSPORTATION, B=INSTALLATION, C=TESTING, D= DISMANTLE, J=CABLE JOINTING, H=DAILY HIRE | [11 empty] | Prepared by:
'H' REW = Registed Electrical Worker with work code at H and work code suffix at 0 or 2
(DSP0101008 REV. 0)