## Sheet1
West / East Region
SIEMENS/KUM SHING ENGINEERING CO., LTD. | [7 empty] | Amendment
Daily Work Record of Contractor's Personnel | [11 empty] | DATE : | 2009-08-26
PO NO. | PROJECT | LOCATION | Region | Nature of | Is CP | Name | Safety | Gang | 'H' REW | Commencement | Responsible | Gang Members | Remarks
|  |  |  | Work* | required? | Of | Document |  | Supervisor |  | Engineer
| NO. |  |  | A/B/C/D/J/H | (y/n) | CP In Charge | Holder(LWC/PTW) | Leader | In Charge | Date | (CLPP)
Active Sites
TBA ( Siemens Project ) | TBA | Waterloo Rd 8 S/S - ( 34220-4 ) | EWR | J - HV | Y | K W Chung 90306833 | K W Chung 90306833 | K W Chung 90306833 | Donny Wong 92831602 ( J-HW-0805 ) | 26/08/2009 ( 09:00 - 14:00 ) | Alex Sien | Yan Wai Shing | B/R 1 x HV Term For CVT Replacement
TBA Siemens Project | TBA | Disney Hollywood Hotel S/S - ( 34578-4 ) - Circuit On : PBY Sewage PBY | EWR | J - HV | Y | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Donny Wong 92831602 ( J-HW-0817 ) | 26/08/2009 ( 09:00 - 14:00 ) | S F Chow | Chum Kwok Hang | B/R 1 x HV Term For CVT Replacement
4500516559 ( 3544 New Project ) | TBA | Nathan Rd 63 A S/S - TST - ( 36593-2 ) - Tx D3 | EWR | J-LV | N | No Needed | No Needed | Ng Wing Shuen 91596143 | C Y Tse 98197931 C K Chu 97536168 | 26/08/2009 ( 09:00 - 19:00 ) | Alex Chow | Cheung Fai Kwan Kin Wing Tsang Ku To | 12 x 960 S/C Tx D3 To ACB @ ?M 1 Set x MCT ( ACB Only )
4500516756 ( 3544 New Project ) | TBA | Nathan Rd 63 B S/S - TST - ( 36594-7 ) - Tx D4 | EWR | J-LV | N | No Needed | No Needed | Ng Wing Shuen 91596143 | C Y Tse 98197931 C K Chu 97536168 | 26/08/2009 ( 09:00 - 19:00 ) | Alex Chow | Cheung Fai Kwan Kin Wing Tsang Ku To | 12 x 960 S/C Tx D4 To ACB @ ?M 1 Set x MCT ( ACB Only )
4500549324 ( 3544 New Project ) | TBA | KIL 11146 T/S S/S - Hoi Fai Rd - ( 36397-9 ) - L/Tx | EWR | J-HV | N | No Needed | No Needed | W S Yan Chung 94606064 | C Y Tse 98197931 C K Chu 97536168 | 26/08/2009 ( 15:00 - 19:00 ) | T Y Sin | Chum Kok Hang Yan Wai Shing Chan Yeung Lai | Breaking & Removing 2 x 95 S/C HV Term RMU To L/Tx
DAILY HIRE
A=TRANSPORTATION, B=INSTALLATION, C=TESTING, D= DISMANTLE, J=CABLE JOINTING, H=DAILY HIRE | [11 empty] | Prepared by:
'H' REW = Registed Electrical Worker with work code at H and work code suffix at 0 or 2
(DSP0101008 REV. 0)