## Sheet1
West / East Region
SIEMENS/KUM SHING ENGINEERING CO., LTD. | [7 empty] | Amendment
Daily Work Record of Contractor's Personnel | [11 empty] | DATE : | 2009-08-27
PO NO. | PROJECT | LOCATION | Region | Nature of | Is CP | Name | Safety | Gang | 'H' REW | Commencement | Responsible | Gang Members | Remarks
|  |  |  | Work* | required? | Of | Document |  | Supervisor |  | Engineer
| NO. |  |  | A/B/C/D/J/H | (y/n) | CP In Charge | Holder(LWC/PTW) | Leader | In Charge | Date | (CLPP)
Active Sites
TBA ( Siemens Project ) | TBA | KCRC E.Rail TST Stn - ( 34216-3 ) Bd 2 - P2 | EWR | J - HV | Y | K W Chung 90306833 | K W Chung 90306833 | K W Chung 90306833 | Donny Wong 92831602 ( J-HW-0806 ) | 27/08/2009 ( 09:00 - 14:00 ) | T F Ngai | Yan Wai Shing | B/R 1 x HV Term For CVT Replacement
TBA Siemens Project | TBA | Penny Bay IR P/P Station S/S - ( 34578-4 ) - Circuit On : Disney Theme Part | EWR | J - HV | Y | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Donny Wong 92831602 ( J-HW-0818 ) | 27/08/2009 ( 09:00 - 14:00 ) | S F Chow | Chum Kwok Hang | B/R 1 x HV Term For CVT Replacement
4500516756 ( 3544 New Project ) | TBA | Nathan Rd 63 B S/S - TST - ( 36594-7 ) - Tx D5 | EWR | J-LV | N | No Needed | No Needed | Ng Wing Shuen 91596143 | C Y Tse 98197931 C K Chu 97536168 | 27/08/2009 ( 09:00 - 19:00 ) | Alex Chow | Cheung Fai Kwan Kin Wing Tsang Ku To | 12 x 960 S/C Tx D5 To LVB @ ?M LVB Only
4500516756 ( 3544 New Project ) | TBA | Nathan Rd 63 B S/S - TST - ( 36594-7 ) - Tx D5 | EWR | J-LV | N | No Needed | No Needed | Ng Wing Shuen 91596143 | C Y Tse 98197931 C K Chu 97536168 | 27/08/2009 ( 09:00 - 19:00 ) | Alex Chow | Cheung Fai Kwan Kin Wing Tsang Ku To | 12 x 960 S/C LVB To ACB @ ?M 1 Set x MCT
TBA ( 3544 New Project ) | TBA | Tsun Yip St 58 S/S - ( 03630-9 ) - Panel 4 & 5 | EWR | J-HV | Y | C C Tang 96403379 | C C Tang 96403379 | H Y Tang 62739940 | K W Leung / S H Kwok 63057587 | 27/08/2009 ( 22:00 - 05:00 ) | K H Wong | M W Chow Ng Kenneth | Breaking & Remaking 2 x HV Term For Busbar Extension
DAILY HIRE
A=TRANSPORTATION, B=INSTALLATION, C=TESTING, D= DISMANTLE, J=CABLE JOINTING, H=DAILY HIRE | [11 empty] | Prepared by:
'H' REW = Registed Electrical Worker with work code at H and work code suffix at 0 or 2
(DSP0101008 REV. 0)