## Sheet1
West / East Region
SIEMENS/KUM SHING ENGINEERING CO., LTD. | [7 empty] | Amendment
Daily Work Record of Contractor's Personnel | [11 empty] | DATE : | 2009-08-29
PO NO. | PROJECT | LOCATION | Region | Nature of | Is CP | Name | Safety | Gang | 'H' REW | Commencement | Responsible | Gang Members | Remarks
|  |  |  | Work* | required? | Of | Document |  | Supervisor |  | Engineer
| NO. |  |  | A/B/C/D/J/H | (y/n) | CP In Charge | Holder(LWC/PTW) | Leader | In Charge | Date | (CLPP)
Active Sites
4500515273 ( 3544 New Project ) | TBA | C S Wan Wholsale Market S/S - ( 15232-7 ) - Tx D2 | EWR | J-LV | Y | K W Kwan 97503319 | K W Kwan 97503319 | Ng Wing Shuen 91596143 | C Y Tse 98197931 C K Chu 97536168 | 29/08/2009 ( 09:00 - 18:00 ) | Raymond Yeung | Cheung Fai Kwan Kin Wing Tsang Ku To | 12 x 960 S/C Tx D2 To ACB @ 8M 1 Set x MCT
TBA ( 3544 New Project ) | TBA | Silver Strand PKG S/S - ( 04883-7 ) - L/Tx | NR | J-HV | N | No Needed | No Needed | K W Chung 90306833 | C Y Tse 98197931 C K Chu 97536168 ( J-HW-0826 ) | 29/08/2009 ( 09:00 - 17:00 ) | Tony Lam | Chum Kok Hang Yan Wai Shing Chan Yeung Lai | 2 x 95 S/C HV Term P3 To L/Tx 3 x 7M x 95 S/C
TBA ( 3544 New Project ) | TBA | Kau To - Lai Ping Rd PKG S/S - Shatin - ( 36604-5 ) - L/Tx | NR | J-HV | N | No Needed | No Needed | K W Chung 90306833 | C Y Tse 98197931 C K Chu 97536168 ( J-HW-0827 ) | 29/08/2009 ( 09:00 - 17:00 ) | Tony Lam | Chum Kok Hang Yan Wai Shing Chan Yeung Lai | 2 x 95 S/C HV Term P4 To L/Tx 3 x 7M x 95 S/C
DAILY HIRE
A=TRANSPORTATION, B=INSTALLATION, C=TESTING, D= DISMANTLE, J=CABLE JOINTING, H=DAILY HIRE | [11 empty] | Prepared by:
'H' REW = Registed Electrical Worker with work code at H and work code suffix at 0 or 2
(DSP0101008 REV. 0)