## Sheet1
West / East Region
SIEMENS/KUM SHING ENGINEERING CO., LTD. | [7 empty] | Amendment
Daily Work Record of Contractor's Personnel | [11 empty] | DATE : | 2010-02-03
PO NO. | PROJECT | LOCATION | Region | Nature of | Is CP | Name | Safety | Gang | 'H' REW | Commencement | Responsible | Gang Members | Remarks
|  |  |  | Work* | required? | Of | Document |  | Supervisor |  | Engineer
| NO. |  |  | A/B/C/D/J/H | (y/n) | CP In Charge | Holder(LWC/PTW) | Leader | In Charge | Date | (CLPP)
Active Sites
4500472578 ( 3544 New Project ) | TBA | Sha Tsui Rd 52 - 58 B S/S - TW - ( 36272-7 ) - Tx D3 | EWR | J-LV | Y | K W Kwan 97503319 | K W Kwan 97503319 | Ng Wing Shuen 91596143 | S H Kwok 90476138 | 03/02/2010 ( 09:00 - 17:00 ) | W K Cho | Cheung Fai Kwan Kin Wing Tsang Ku To | 12 x 960 S/C Tx D3 To ACB @ 13M 1 Set x MCT
TBA Siemens Project | TBA | H K Rattan S/S - KT&WS ( 04021-6 ) Circuit On : Hung To Rd 12 Panel - 4 | EWR | J - HV | Y | Yeung Chiu Wing 61732638 | Yeung Chiu Wing 61732638 | Yeung Chiu Wing 61732638 | Donny Wong 92831602 ( J-HW-1200 ) | 03/02/2009 ( 09:00 - 13:00 ) | K K Lai | Chum Kwok Hang Fung Ho Shing | B/R 1 x HV Term For CVT Replacement
TBA Siemens Project ( Cancelled ) | TBA | Garden Bakery S/S - SP ( 01532-2 ) Circuit On : North Kowloon Magistracy Panel - 1 | EWR | J - HV | Y | K W Chung 90306833 | K W Chung 90306833 | K W Chung 90306833 | Donny Wong 92831602 ( J-HW-1201 ) | 03/02/2009 ( 09:00 - 13:00 ) | K M Yeung | Chan Hei Long Cheuk Pui Kuen | B/R 1 x HV Term For CVT Replacement
TBA Siemens Project | TBA | Cheung Chau North S/S - LT ( 16069-4 ) Circuit On : Police Station S/S Panel - 2 | EWR | J - HV | Y | K W Chung 90306833 | K W Chung 90306833 | K W Chung 90306833 | Donny Wong 92831602 ( J-HW-1201 ) | 03/02/2009 ( 09:00 - 13:00 ) | S F Chow | Chan Hei Long Cheuk Pui Kuen | B/R 1 x HV Term For CVT Replacement
TBA Siemens Project | TBA | Lion Rock Tunnel PKG 'B' S/S - ST ( 34270-7 ) Circuit On : Hin Keng Comm Complex 'B' Panel - 2 | EWR | J - HV | Y | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Donny Wong 92831602 ( J-HW-1202 ) | 03/02/2009 ( 09:00 - 13:00 ) | S O Man | Chan Yeung Lai Wong Hoi Hin | B/R 1 x HV Term For CVT Replacement
DAILY HIRE
A=TRANSPORTATION, B=INSTALLATION, C=TESTING, D= DISMANTLE, J=CABLE JOINTING, H=DAILY HIRE | [11 empty] | Prepared by:
'H' REW = Registed Electrical Worker with work code at H and work code suffix at 0 or 2
(DSP0101008 REV. 0)