## Sheet1
West / East Region
SIEMENS/KUM SHING ENGINEERING CO., LTD. | [7 empty] | Amendment
Daily Work Record of Contractor's Personnel | [11 empty] | DATE : | 2010-02-10
PO NO. | PROJECT | LOCATION | Region | Nature of | Is CP | Name | Safety | Gang | 'H' REW | Commencement | Responsible | Gang Members | Remarks
|  |  |  | Work* | required? | Of | Document |  | Supervisor |  | Engineer
| NO. |  |  | A/B/C/D/J/H | (y/n) | CP In Charge | Holder(LWC/PTW) | Leader | In Charge | Date | (CLPP)
Active Sites
TBA Siemens Project ( Cancelled ) | TBA | S/S - LT ( 16069-4 ) Circuit On : Panel - 3 | EWR | J - HV | Y | K W Chung 90306833 | K W Chung 90306833 | K W Chung 90306833 | Donny Wong 92831602 ( J-HW-1212 ) | 10/02/2009 ( 09:00 - 13:00 ) | S F Chow | Chan Hei Long Cheuk Pui Kuen | B/R 1 x HV Term For CVT Replacement
TBA Siemens Project ( Cancelled ) | TBA | Garden Bakery S/S - SP ( 01532-2 ) Circuit On : North Kowloon Magistracy Panel - 1 | EWR | J - HV | Y | K W Chung 90306833 | K W Chung 90306833 | K W Chung 90306833 | Donny Wong 92831602 ( J-HW-1201 ) | 10/02/2009 ( 09:00 - 13:00 ) | K M Yeung | Chan Hei Long Cheuk Pui Kuen | B/R 1 x HV Term For CVT Replacement
TBA Siemens Project | TBA | Cheung Wah St S/S - SP ( 01610-1 ) Circuit On : Cheung Sha Wan Indoor Games Hall Panel - 5 | EWR | J - HV | Y | Yeung Chiu Wing 61732638 | Yeung Chiu Wing 61732638 | Yeung Chiu Wing 61732638 | Donny Wong 92831602 ( J-HW-1201 ) | 10/02/2009 ( 09:00 - 13:00 ) | K M Yeung | Fung Ho Shing | B/R 1 x HV Term For CVT Replacement
TBA Siemens Project ( Cancelled ) | TBA | Cheung Chau Lot 1833 S/S - LT ( 16069-4 ) Circuit On : CCN-011 Panel - 2 | EWR | J - HV | Y | K W Chung 90306833 | K W Chung 90306833 | K W Chung 90306833 | Donny Wong 92831602 ( J-HW-1213 ) | 10/02/2009 ( 14:00 - 17:00 ) | S F Chow | Chan Hei Long Cheuk Pui Kuen | B/R 1 x HV Term For CVT Replacement
TBA Siemens Project ( Cancelled ) | TBA | Cheung Chau Lot 1833 S/S - LT ( 16069-4 ) Circuit On : Police Station Path Panel - 1 | EWR | J - HV | Y | K W Chung 90306833 | K W Chung 90306833 | K W Chung 90306833 | Donny Wong 92831602 ( J-HW-1337 ) | 10/02/2009 ( 14:00 - 17:00 ) | S F Chow | Chan Hei Long Cheuk Pui Kuen | B/R 1 x HV Term For CVT Replacement
TBA Siemens Project | TBA | Area 110 Blk 5 S/S - YL ( 24663-9 ) Circuit On : Area 110 Blk 4 Panel - 4 | EWR | J - HV | Y | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Donny Wong 92831602 ( J-HW-1214 ) | 10/02/2009 ( 09:00 - 13:00 ) | Dick Lau | Chan Yeung Lai Wong Hoi Hin | B/R 1 x HV Term For CVT Replacement
TBA ( 3544 New Project ) | TBA | Global Gateway A S/S - Yeung Uk Rd 168 - TW - ( 18424-9 ) - Tx D1 | EWR | J-HV | Y | Chan Yeung Lai 69705055 | Chan Yeung Lai 69705055 | K W Chung 90306833 | C Y Tse 98197931 | 10/02/2010 ( 09:00 - 15:00 ) | C M Wong | Chum Kok Hang Chan Hei Long Chan Yeung Lai Yeung Chiu Wing Ng Yat Sing | Breaking & Removing 2 x 95 3/C HV Term Tx D1
TBA ( 3544 New Project ) | TBA | Global Gateway A S/S - Yeung Uk Rd 168 - TW - ( 18424-9 ) - Tx D1 | EWR | J-LV | Y | TBA ( 3544 New Project ) | TBA ( 3544 New Project ) | K W Chung 90306833 | C Y Tse 98197931 | 10/02/2010 ( 09:00 - 15:00 ) | C M Wong | Chum Kok Hang Chan Hei Long Chan Yeung Lai Yeung Chiu Wing Ng Yat Sing | Disconnecting 10 x 960 S/C Tx D1 To ACB
TBA ( 3544 New Project ) | TBA | Forture Villa S/S - Wo Shun Lane - Cheung Chau ( 14569-4 ) - Tx Replacement | EWR | J-HV | Y | Chan Yeung Lai 69705055 | Chan Yeung Lai 69705055 | K W Chung 90306833 | Michael Tang 94228077 ( J-HW-1338 ) | 10/02/2010 ( 10:00 - 16:00 ) | S F Chow | Chum Kok Hang Lai Man Kuen Chan Yeung Lai Or Kin Ming Ng Yat Sing | Breaking & Removing 2 x 95 3/C HV Term P3 To L/Tx
TBA ( 3544 New Project ) | TBA | Forture Villa S/S - Wo Shun Lane - Cheung Chau ( 14569-4 ) - Tx Replacement | EWR | J-HV | Y | Chan Yeung Lai 69705055 | Chan Yeung Lai 69705055 | K W Chung 90306833 | Michael Tang 94228077 ( J-HW-1338 ) | 10/02/2010 ( 10:00 - 16:00 ) | S F Chow | Chum Kok Hang Chan Hei Long Chan Yeung Lai Yeung Chiu Wing Ng Yat Sing | 2 x 95 3/C HV Term Panel 3 To L/Tx 1 x 10M x 95 3/C
TBA ( 3544 New Project ) | TBA | Forture Villa S/S - Wo Shun Lane - Cheung Chau ( 14569-4 ) - Tx Replacement | EWR | J-LV | Y | K W Chung 90306833 | K W Chung 90306833 | K W Chung 90306833 | Michael Tang 94228077 | 10/02/2010 ( 10:00 - 16:00 ) | S F Chow | Chum Kok Hang Chan Hei Long Chan Yeung Lai Yeung Chiu Wing Ng Yat Sing | Disconnecting & Reconnecting 10 x 960 S/C L/Tx To LVB
DAILY HIRE
A=TRANSPORTATION, B=INSTALLATION, C=TESTING, D= DISMANTLE, J=CABLE JOINTING, H=DAILY HIRE | [11 empty] | Prepared by:
'H' REW = Registed Electrical Worker with work code at H and work code suffix at 0 or 2
(DSP0101008 REV. 0)