## Sheet1
West / East Region
SIEMENS/KUM SHING ENGINEERING CO., LTD.
Daily Work Record of Contractor's Personnel | [11 empty] | DATE : | 2010-02-13
PO NO. | PROJECT | LOCATION | Region | Nature of | Is CP | Name | Safety | Gang | 'H' REW | Commencement | Responsible | Gang Members | Remarks
|  |  |  | Work* | required? | Of | Document |  | Supervisor |  | Engineer
| NO. |  |  | A/B/C/D/J/H | (y/n) | CP In Charge | Holder(LWC/PTW) | Leader | In Charge | Date | (CLPP)
Active Sites
TBA ( 3544 New Project ) | TBA | Kowloon City Market S/S - KC&WS ( 03933-9 ) Tx D1 | EWR | J - LV | Y | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | K W Chung 90306833 | K W Leung 63057587 | 13/02/2009 ( 23:30 - 04:00 ) |  | Chum Kok Hang Chan Hei Long Chan Yeung Lai Yeung Chiu Wing Ng Yat Sing | Disconnecting 10 x 960 S/C ( Both End )
TBA ( 3544 New Project ) | TBA | Kowloon City Market S/S - KC&WS ( 03933-9 ) Tx D2 | EWR | J - LV | Y | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | K W Chung 90306833 | K W Leung 63057587 | 13/02/2009 ( 23:30 - 04:00 ) |  | Chum Kok Hang Chan Hei Long Chan Yeung Lai Yeung Chiu Wing Ng Yat Sing | Disconnecting 10 x 960 S/C ( Both End )
TBA ( 3544 New Project ) | TBA | Ngau Chi Market Complex S/S - KC&WS ( 02884-4 ) Tx D1 | EWR | J - LV | Y | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | K W Chung 90306833 | K W Leung 63057587 | 13/02/2009 ( 23:30 - 04:00 ) |  | Chum Kok Hang Chan Hei Long Chan Yeung Lai Yeung Chiu Wing Ng Yat Sing | Reconnecting & Removing 10 x 960 S/C Tx To ACB 4 x 960 S/C From Tx To LVB
TBA ( 3544 New Project ) | TBA | Ngau Chi Market Complex S/S - KC&WS ( 02884-4 ) Tx D2 | EWR | J - LV | Y | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | K W Chung 90306833 | K W Leung 63057587 | 13/02/2009 ( 23:30 - 04:00 ) |  | Chum Kok Hang Chan Hei Long Chan Yeung Lai Yeung Chiu Wing Ng Yat Sing | Reconnecting & Removing 10 x 960 S/C Tx To ACB
TBA ( 3544 New Project ) | TBA | Po On Market B S/S - SSPo ( 01590-5 ) Tx D1 | EWR | J - LV | Y | K W Kwan 97503319 | K W Kwan 97503319 | Ng Wing Shuen 91596143 | C Y Tse 98197931 | 13/02/2009 ( 23:30 - 04:00 ) | N K Tai | Cheung Fai Kwan Kin Wing Tsang Ku To | Reconnecting & Removing 10 x 960 S/C
TBA ( 3544 New Project ) | TBA | Po On Market B S/S - SSPo ( 01590-5 ) Tx D2 | EWR | J - LV | Y | K W Kwan 97503319 | K W Kwan 97503319 | Ng Wing Shuen 91596143 | C Y Tse 98197931 | 13/02/2009 ( 23:30 - 04:00 ) | N K Tai | Cheung Fai Kwan Kin Wing Tsang Ku To | Reconnecting & Removing 10 x 960 S/C
DAILY HIRE
A=TRANSPORTATION, B=INSTALLATION, C=TESTING, D= DISMANTLE, J=CABLE JOINTING, H=DAILY HIRE | [11 empty] | Prepared by:
'H' REW = Registed Electrical Worker with work code at H and work code suffix at 0 or 2
(DSP0101008 REV. 0)