## Sheet1
West / East Region
SIEMENS/KUM SHING ENGINEERING CO., LTD. | [7 empty] | Amendment
Daily Work Record of Contractor's Personnel | [11 empty] | DATE : | 2010-02-17
PO NO. | PROJECT | LOCATION | Region | Nature of | Is CP | Name | Safety | Gang | 'H' REW | Commencement | Responsible | Gang Members | Remarks
|  |  |  | Work* | required? | Of | Document |  | Supervisor |  | Engineer
| NO. |  |  | A/B/C/D/J/H | (y/n) | CP In Charge | Holder(LWC/PTW) | Leader | In Charge | Date | (CLPP)
Active Sites
TBA ( 3544 New Project ) | TBA | Kong Nam I/B B S/S - TW ( 12227-8 ) Tx D1 | EWR | J - LV | Y | K W Kwan 97503319 | K W Kwan 97503319 | Ng Wing Shuen 91596143 | Michael Tang 94228077 | 17/02/2009 ( 20:00 - 22:00 ) | K K Leung | Cheung Fai Kwan Kin Wing Tsang Ku To | Disconnecting 4 x 185 S/C Reconnecting 10 x 960 S/C ( One End ) CT Installetion
TBA ( 3544 New Project ) | TBA | Kong Nam I/B F S/S - TW ( 09077-7 ) Tx D3 | EWR | J - LV | Y | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | K W Chung 90306833 | Michael Tang 94228077 | 17/02/2009 ( 20:00 - 22:00 ) | K K Leung | Chum Kok Hang Chan Hei Long Chan Yeung Lai Yeung Chiu Wing Ng Yat Sing | Disconnecting 4 x 185 S/C Reconnecting 10 x 960 S/C ( One End ) CT Installetion
DAILY HIRE
A=TRANSPORTATION, B=INSTALLATION, C=TESTING, D= DISMANTLE, J=CABLE JOINTING, H=DAILY HIRE | [11 empty] | Prepared by:
'H' REW = Registed Electrical Worker with work code at H and work code suffix at 0 or 2
(DSP0101008 REV. 0)