## Sheet1
West / East Region
SIEMENS/KUM SHING ENGINEERING CO., LTD. | [7 empty] | Amendment
Daily Work Record of Contractor's Personnel | [11 empty] | DATE : | 2010-02-26
PO NO. | PROJECT | LOCATION | Region | Nature of | Is CP | Name | Safety | Gang | 'H' REW | Commencement | Responsible | Gang Members | Remarks
|  |  |  | Work* | required? | Of | Document |  | Supervisor |  | Engineer
| NO. |  |  | A/B/C/D/J/H | (y/n) | CP In Charge | Holder(LWC/PTW) | Leader | In Charge | Date | (CLPP)
Active Sites
TBA Siemens Project | TBA | Pok Wai Pumping Station S/S - YL ( 29339-8 ) Circuit On : Pok Wai Package Panel - 3 | EWR | J - HV | Y | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Ip Ka Chun 98410558 | Donny Wong 92831602 ( J-HW-1231 ) | 26/02/2009 ( 09:00 - 13:00 ) | Dick Lau | Chan Yeung Lai Wong Hoi Hin | B/R 1 x HV Term For CVT Replacement
TBA Siemens Project | TBA | Millennium City Ph 5 B Bd A S/S - KT&WS ( 34494-8 ) Circuit On : Millennium City Ph 5 B Bd B Panel - 3 | EWR | J - HV | Y | Yeung Chiu Wing 61732638 | Yeung Chiu Wing 61732638 | Yeung Chiu Wing 61732638 | Donny Wong 92831602 ( J-HW-1228 ) | 26/02/2009 ( 09:00 - 13:00 ) | K L Leung | Chum Kwok Hang Fung Ho Shing | B/R 1 x HV Term For CVT Replacement
4500579959 ( 3544 New Project ) | TBA | HKUST Academic Bldg Ext S/S - Shatin - ( 36751-2 ) - L/Tx | EWR | J-HV | N | No Needed | No Needed | K W Chung 90306833 | C K Chu 97536181 ( J-HW-1339 ) | 26/02/2010 ( 14:00 - 17:00 ) | Lewis Chung | Chum Kok Hang Chan Hei Long Chan Yeung Lai Yeung Chiu Wing Ng Yat Sing | 2 x 95 3/C HV Term Panel 3 To L/Tx 1 x 12M x 95 3/C
DAILY HIRE
A=TRANSPORTATION, B=INSTALLATION, C=TESTING, D= DISMANTLE, J=CABLE JOINTING, H=DAILY HIRE | [11 empty] | Prepared by:
'H' REW = Registed Electrical Worker with work code at H and work code suffix at 0 or 2
(DSP0101008 REV. 0)