## Sheet1
West / East Region
SIEMENS/KUM SHING ENGINEERING CO., LTD.
Daily Work Record of Contractor's Personnel | [11 empty] | DATE : | 2010-02-28
PO NO. | PROJECT | LOCATION | Region | Nature of | Is CP | Name | Safety | Gang | 'H' REW | Commencement | Responsible | Gang Members | Remarks
|  |  |  | Work* | required? | Of | Document |  | Supervisor |  | Engineer
| NO. |  |  | A/B/C/D/J/H | (y/n) | CP In Charge | Holder(LWC/PTW) | Leader | In Charge | Date | (CLPP)
Active Sites
TBA ( 3544 New Project ) | TBA | Everest Bldg S/S - Pilkem St / Jordan Rd ( 03855-0 ) Tx Replacement | EWR | J - LV | Y | K W Kwan 97503319 | K W Kwan 97503319 | Ng Wing Shuen 91596143 | Michael Tang 94228077 | 28/02/2009 ( 23:59 - 05:00 ) | Alex Sien | Cheung Fai Kwan Kin Wing Tsang Ku To | Reconnecting & Reconnecting 7 x 960 S/C ( One End )
DAILY HIRE
A=TRANSPORTATION, B=INSTALLATION, C=TESTING, D= DISMANTLE, J=CABLE JOINTING, H=DAILY HIRE | [11 empty] | Prepared by:
'H' REW = Registed Electrical Worker with work code at H and work code suffix at 0 or 2
(DSP0101008 REV. 0)